## Gantt Chart - Manual Duration
2015 TIPS Open Source Message Switch Project - Grant # 2015-DG-SEARC-01
Task Name | Responsible Party-SEARCH | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete
Grant and Project Administration | Mark | 2017-01-02 | 2019-03-29 | 816 | 408 | 408 | 50%
Vendor Contract Administration | Andrew | 2017-05-01 | 2019-03-29 | 697 | 697 | 0 | 100%
RFP and Approvals | Andrew/Mike | 2017-05-01 | 2018-02-01 | 276 | 276 | 0 | 100%
GCOM Contract | Andrew | 2018-02-03 | 2019-03-29 | 419 | 419 | 0 | 100%
Innovatio Contract | Andrew | 2018-02-05 | 2019-03-29 | 417 | 417 | 0 | 100%
Requirements Analysis | Andrew | 2017-03-01 | 2018-07-20 | 506 | 285.5286 | 220.4714 | 56.43%
Project Orientation and Re-Initiation | Andrew/Mike | 2017-12-28 | 2018-03-28 | 90 | 45 | 45 | 50%
Developer Face-to-Face | Andrew/Mike | 2018-02-01 | 2018-02-23 | 22 | 22 | 0 | 100%
Business Requirements Acceptance | Mike/Jim | 2017-03-01 | 2018-05-23 | 448 | 224 | 224 | 50%
SME Meeting(s) | Mike | 2017-03-01 | 2018-05-05 | 430 | 279.5 | 150.5 | 65%
Client Requirements - Data Models | Jim | 2018-01-22 | 2018-05-23 | 121 | 54.45 | 66.55 | 45%
Service Specifications | Jim | 2018-02-22 | 2018-06-22 | 120 | 42 | 78 | 35%
Features/Backlog List | Andrew/Mike | 2018-02-22 | 2018-07-20 | 148 | 74 | 74 | 50%
Design and Development | Andrew/Mike | 2018-01-05 | 2018-08-01 | 208 | 38.1333 | 169.8667 | 18.33%
Architecture (see backlog) |  | 2018-01-05 | 2018-05-05 | 120 | 54 | 66 | 45%
Software (see backlog) |  | 2018-02-23 | 2018-07-16 | 143 | 14.3 | 128.7 | 10%
User Acceptance Testing |  | 2018-07-01 | 2018-08-15 | 45 | 0 | 45 | 0%
Deployment | Andrew | 2018-05-06 | 2018-12-13 | 221 | 0 | 221 | 0%
Architecture and Databases |  | 2018-05-06 | 2018-08-04 | 90 | 0 | 90 | 0%
Message Switch (Intermediary) |  | 2018-07-17 | 2018-10-15 | 90 | 0 | 90 | 0%
Connectors |  | 2018-07-30 | 2018-11-27 | 120 | 0 | 120 | 0%
Adapters |  | 2018-08-15 | 2018-12-13 | 120 | 0 | 120 | 0%
Maintenance and Sustainability | Andrew | 2018-12-14 | 2019-03-31 | 107 | 0 | 107 | 0%
Project End | All | 2019-03-31 | 2019-04-01 | 1 | 0.3746 | 0.6254 | 37.46%
[8 empty] | Key: | Calculated Cell | Manual Entry Cell
[9 empty] | These cells will be automatically calculated based on the inputs on other cells. | These cells require manual input so the calculated cells have data to work with.
Formulas:
End Date = IF(ISBLANK([Duration (Days)]),"",[Duration (Days)]+[Start Date])